## Test_Scenario
Test Case Id | Functionality Id | Test Case Summary | Step | Test data | Expected Result | Actual Result
1 | 1 | check website URL | 1) https://www.saucedemo.com 2) press enter key | NA | To open the website | As per expected Result
2 | 2 | check login button with the unique username and strong password | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: s@uce_demo1 password: secret_sauce | to logged in user in the website successfully | As per expected result
3 | 2 | check login button with password which is visible or encrypted | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: s@uce_demo1 password: ********** | to diplay the password in asterisk symbol | As per expected result
4 | 3 | check side menu | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on side menu | NA | To open the side menu | As per expected result
5 | 200 | check about menu | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on side menu 5) click on all item menu 6) click on about menu | NA | To open the all details about their own website | As per expected result
6 | 301 | check close icon | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on side menu 5) click on all item menu 6) click on about menu 7) click on reset app state 8) click on close icon | NA | to close the side menu | As per expected result
7 | 401 | check continue shopping button | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click continue shopping button | NA | To open all the product details | As per expected result
8 | 402 | check filter option | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on continue shopping button 6) click on filter option | Filters: Name(A to Z) Name(Z to A) Price(low to high) Price(high to low) | All the filter options are working properly | As per expected result
9 | 403 | check image link | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on continue shopping button 6) click on filter option 7) click on image link | NA | To open the selected image with its details | As per expected result
10 | 404 | check addtocart button | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on continue shopping button 6) click on filter option 7) click on image link 8) click on addtocart button | NA | To insert the selected item/product into the cart | As per expected result
11 | 405 | check remove button | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on continue shopping button 6) click on filter option 7) click on image link 8) click on remove button | NA | To remove the selected item/product from the cart | As per expected result
12 | 406 | check back to product link | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on continue shopping button 6) click on filter option 7) click on image link 8) click on remove button 9) click on back to product link | NA | To open the previous page after clicking back to product link | As per expected result
13 | 407 | check product text link | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on continue shopping button 6) click on filter option 7) click on image link 8) click on remove button 9) click on back to product link 10) click on product text link | NA | To display the details of selected product | As per expected result
14 | 408 | check addtocart button | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on continue shopping button 6) click on filter option 7) click on image link 8) click on remove button 9) click on back to product link 10) click on product text link 11) click on addtocart button | NA | To insert the selected item/product into the cart | As per expected result
15 | 409 | check remove button | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on continue shopping button 6) click on filter option 7) click on image link 8) click on remove button 9) click on back to product link 10) click on product text link 11) click on remove button | NA | To remove the selected item/product from the cart | As per expected result
16 | 410 | check checkout button | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | NA | To checkout from addtocart to checkout page | As per expected result
17 | 410 | check first name, last name and zip code with correct value | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: bhoomi Last name: prajapati zip code: 380051 | To display the checkout info(bill) | As per expected result
18 | 410 | check zip/postol code only with digits | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: bhoomi Last name: prajapati zip code: 380051 | To display the checkout info(bill) | As per expected result
19 | 411 | check continue button | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button 6) click on continue button | NA | To display the complete details about the purchased item/product | As per expected result
20 | 412 | check finish button | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button 6) click on continue button 7) click on finish button | NA | To open the thank you page successfully | As per expected result
21 | 413 | check back to home button | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button 6) click on continue button 7) click on finish button 8) click on back to home button | NA | To redirect us into the home page succefully | As per expected result
22 | 500 | check social media icon in footer | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button 6) click on continue button 7) click on finish button 8) click on back to home button 9) click on social media icons | social media icons: 1) twitter 2) facebook 3) linkdin | all the social media icons work properly | As per expected result
23 | 600 | check logout | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on side menu 5) click on all item menu 6) click on about menu 7) click on reset app state 8) click on logout | NA | while clicking on logout, it logged out user from the website | As per expected result

## Defect_Report
Defect Id | Test case Id | Defect Summary | Reproduced Step | Test Data | Defect Types | Defect severity | Defect priority | Expected Result | Actual Result | Tester Name | Attachment | Status
1 | 2 | check Login button | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: standard_user password: secret_sauce | Functionality defect, Security defect | High | High | To open the user dashboard with proper details | As per expected Result but we can't see the user details | suwarna | https://drive.google.com/file/d/10Q-Osj37l-LBSdG5aLmb8CnVrP3XlEM9/view?usp=sharing | OPEN
2 | 2 | check Login button with wrong value | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username:dffsdrsgrfgvdx password: dvdvfdvsvzv | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | To display the validation message but not to see properly | suwarna | https://drive.google.com/file/d/1w_36SVim377zdkYrENA7yrHMae47hdmx/view?usp=sharing | OPEN
3 | 2 | check Login button with null / blank value | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: password: | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message | suwarna | https://drive.google.com/file/d/1vMb_WbIGV1L5wulbM7WgmStwPjHWY26G/view?usp=sharing | OPEN
4 | 2 | check login button with username is required but password is blank | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: standard_user password: | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1Rmh4Bi0QJCeCEmKYXk76ktU4niOZjyB7/view?usp=sharing | OPEN
5 | 2 | check login button with username is blank but password is required | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: password: secret_sauce | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1IbspYgG3_ZjJKkNQrjYEeugNWKlApShV/view?usp=sharing | OPEN
6 | 2 | check login button with whitespace in username | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: password: secret_sauce | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1HsOuTh62i4GOvRmTL2Z3_rs7v_nVBE7n/view?usp=sharing | OPEN
7 | 2 | check login button with legth of username | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: cdcdvfvsvfdsdfrsfvfvxvfddxvdvvvddds password: secret_sauce | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1x9NXJKwrwhs3DAdPZ_uOfbWlU6bqbeE9/view?usp=sharing | OPEN
8 | 2 | check login button with whitespace in between the username | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: efe fefef ff password: secret_sauce | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1O1JkPJ84ge1_1vgz_Ypqh6YaSD0p4niW/view?usp=sharing | OPEN
9 | 2 | check login button which start with the special character in username | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: @testing password: secret_sauce | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1aXxorAqCcnxwawlDZzKRWBajYicmSWdA/view?usp=sharing | OPEN
10 | 2 | check login button with e-mail address | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: saucedemo@gmail.com password: secret_sauce | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1GCW_HHuqfdrMg8SHA9vWdMSzGtd3X_WW/view?usp=sharing | OPEN
11 | 2 | check login button with only digits in username | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: 23456798 password: secret_sauce | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1S1-kzH1nHTqXrYD7ogpff1WF__0LakjW/view?usp=sharing | OPEN
12 | 2 | check login button with length of password | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: s@uce_demo1 password: secret_sauce12dcdcvfdvgftbdbgbdbdgn | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1o4Fv93iT3pcgSkRk8iniSGSiNyssjWXZ/view?usp=sharing | OPEN
13 | 2 | check login button with password which have eye icon | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | NA | Functionality defect, Usability defect, GUI defect | High | High | to display the password when we click on the eye icon in the password field | There is no eye icon in the password field to see the password | suwarna | https://drive.google.com/file/d/1EnAuhkdxPh42-rduxAea0VZuPVUVNaep/view?usp=sharing | OPEN
14 | 2 | check login button with only digits in paasword | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: s@uce_demo1 password: 12345678 | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1T0stM0FmyBYVR-BHLeGywnn4SP46zUtv/view?usp=sharing | OPEN
15 | 2 | check login button with only alphabets in password | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: s@uce_demo1 password: saucedemocom | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1yWn7fByIWvGyWlXB5KRP-wFrl0WslCKB/view?usp=sharing | OPEN
16 | 2 | check login button with only white-space in password | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: s@uce_demo1 password: | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1cJtT2rhd7d91q0bbKDhcaUbJWEFaDIpV/view?usp=sharing | OPEN
17 | 2 | check login button with only special characters in password | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button | Username: s@uce_demo1 password: @#$%^&*! | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1w6eOXGblqiHjjfobjzwdZygkhb1OgdGi/view?usp=sharing | OPEN
18 | 100 | check all item menu | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on side menu 5) click on all item menu | NA | Functionality defect, Usability defect | High | High | To open the all items pages | its not to open any pages | suwarna | https://drive.google.com/file/d/1713QtJORK7SiMgpD6MyiBq9O8uBLrHHd/view?usp=sharing | OPEN
19 | 300 | check reset app state | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on side menu 5) click on all item menu 6) click on about menu 7) click on reset app state | NA | Functionality defect, Usability defect | Medium | Medium | To open the reset app state menu | its not to open anything | suwarna | https://drive.google.com/file/d/1vhyBrKqyIiX9QbDPqjafVCw4Kdv781tk/view?usp=sharing | OPEN
20 | 400 | check addtocart icon | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon | NA | GUI defect | High | High | to open the addtocart page | As per expected result but its not to see the clickable on icon | suwarna | https://drive.google.com/file/d/17lDw_n13J0wom4beUAUWGXMJf_HMYlML/view?usp=sharing | OPEN
21 | 410 | check first name, last name and zip code with blank value | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: Last name: zip code: | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | To display the validation message but not to see properly | suwarna | https://drive.google.com/file/d/14AlCym75kxAY4RHnQzrPcFs3mP45yx5Y/view?usp=sharing | OPEN
22 | 410 | check first name and last name with special character and digits | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: bh@@mi12 Last name: #raj3@p@ti5 | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | it doesn't display any validation message and successfully redirected to next page which is not acceptable | suwarna | https://drive.google.com/file/d/1QeriB_H9Ffh0ZSxs15ITf4bjn7pvyrTC/view?usp=sharing | OPEN
23 | 410 | check first name and last name only with digits | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: 2344546 Last name: 3435454 | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | it doesn't display any validation message and successfully redirected to next page which is not acceptable | suwarna | https://drive.google.com/file/d/1E7Rx5MlN1X4MmnSWghYtjYwhZXSS4sHK/view?usp=sharing | OPEN
24 | 410 | check first name and last name only with special character | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: @#^$! Last name: %^%%&^ | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | it doesn't display any validation message and successfully redirected to next page which is not acceptable | suwarna | https://drive.google.com/file/d/1yI2CAiNPgOYsF5BZtyxNoJc8cGrLiYt3/view?usp=sharing | OPEN
25 | 410 | check first name and last name with white space | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: Last name: | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | it doesn't display any validation message and successfully redirected to next page which is not acceptable | suwarna | https://drive.google.com/file/d/1zg9IxW32dglREm67eDTGNOzz12R7g8-n/view?usp=sharing | OPEN
26 | 410 | check length of first name and last name | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name :suwarna Last name :shinde | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | it doesn't display any validation message and successfully redirected to next page which is not acceptable | suwarna | https://drive.google.com/file/d/1enfnbeqqLApNcQhdGxP2NqWAvasPZ2RY/view?usp=sharing | OPEN
27 | 410 | check zip/postol code with alphabets | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: suwana Last name: shinde zip code: suwarna | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | it doesn't display any validation message and successfully redirected to next page which is not acceptable | suwarna | https://drive.google.com/file/d/1TOOStQ9qYvcWlbR_dQcw8v-4v8UL26ba/view?usp=sharing | OPEN
28 | 410 | check zip/postol code with alpha-numeric | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: suwarna Last name: shinde zip code: bh0058 | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | it doesn't display any validation message and successfully redirected to next page which is not acceptable | suwarna | https://drive.google.com/file/d/1_FqRa5aKn2HDrpbK1rKnR2IxHx1gRaqC/view?usp=sharing | OPEN
29 | 410 | check the length of zip/postol code | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: suwarna Last name: :shinde zip code: 38000005111111 | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | it doesn't display any validation message and successfully redirected to next page which is not acceptable | suwarna | https://drive.google.com/file/d/11WMte1eWnHCdgIkIKZPE8NpNpUgahuU8/view?usp=sharing | OPEN
30 | 410 | check zip/postol code only with white space | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: suwarna Last name: shinde zip code: | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | it doesn't display any validation message and successfully redirected to next page which is not acceptable | suwarna | https://drive.google.com/file/d/1VLOKMKrQAa7QSL5j69yFpBtcIWxPALIt/view?usp=sharing | OPEN
31 | 410 | check zip/postol code only with special characters | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: suwarna Last name: shinde zip code: $%$^%@@!! | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | it doesn't display any validation message and successfully redirected to next page which is not acceptable | suwarna | https://drive.google.com/file/d/1aDJ7Zle4Trg6SEB56e4QdreUxhLB1QlY/view?usp=sharing | OPEN
32 | 410 | check zip/postol code in digit with hyphen(-) | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: suwarna Last name: shinde zip code: 2314-3556 | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | it doesn't display any validation message and successfully redirected to next page which is not acceptable | suwarna | https://drive.google.com/file/d/1H4Xa-shIgPuCctYpJrVxkmZisH55i27W/view?usp=sharing | OPEN
33 | 410 | check first name is blank but last name and zip code is required | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: Last name: shinde zip code: 380051 | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1OFj3DuBuZjC1Yt5U3OItOTlikH_V8jju/view?usp=sharing | OPEN
34 | 410 | check first name and zip code is required but last name is blank | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: suwarna Last name: zip code: 380051 | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1iC01o1FlyEAwFDrXhYVhcUuMP1vU0WS5/view?usp=sharing | OPEN
35 | 410 | check first name and last name is required but zip code is blank | 1) https://www.saucedemo.com 2) press enter key 3) click on Login button 4) click on addtocart icon 5) click on checkout button | First name: suwarna Last name: shinde zip code: | Functionality defect, Usability defect, GUI defect | High | High | To display the proper validation message | its not to display proper validation message and color property | suwarna | https://drive.google.com/file/d/1Yrm4c26FC4wQRXwLpY_N3--H7CMxsY-y/view?usp=sharing | OPEN